## Sheet1
Online Mentorship Platform for College Students
Task | Start Date | End Date | Duration | Assigned To
Requirement Gathering | 2022-01-25 | 2022-01-28 | 4 | Apurva & Ashlesha
Problem statement Analysis & Design | 2022-01-29 | 2022-02-03 | 6 | Apurva & Ashlesha
Learning technologies required for the project | 2022-02-04 | 2022-02-11 | 8 | Apurva & Ashlesha
Deciding Process Model & Timeline | 2022-02-12 | 2022-02-17 | 6 | Apurva & Ashlesha
Registration Form of Students & Mentors | 2022-02-18 | 2022-02-21 | 4 | Apurva
Email Verification & Login | 2022-02-22 | 2022-02-24 | 3 | Ashlesha
Handling Profile options | 2022-02-25 | 2022-02-27 | 3 | Apurva & Ashlesha
Student Dashboard | 2022-02-28 | 2022-03-04 | 5 | Apurva
Mentor Dashboard | 2022-03-05 | 2022-03-10 | 6 | Ashlesha
Testing Students & Mentors Functionality | 2022-03-11 | 2022-03-13 | 3 | Apurva & Ashlesha
Adding Resources Section | 2022-03-14 | 2022-03-16 | 3 | Apurva
Testing Resources Section | 2022-03-17 | 2022-03-18 | 2 | Ashlesha
Formulas:
Start Date = [End Date, row above]+1