## Sheet1
Task | Start Date | End Date | Duration
Requirement Gathering | 2022-01-25 | 2022-01-28 | 4 | Online Mentorship Platform for College Students
Problem statement Analysis & Design | 2022-01-29 | 2022-02-03 | 6
Learning technologies required for the project | 2022-02-04 | 2022-02-11 | 8
Deciding Process Model & Timeline | 2022-02-12 | 2022-02-17 | 6
Registration Form of Students & Mentors | 2022-02-18 | 2022-02-21 | 4
Email Verification & Login | 2022-02-22 | 2022-02-24 | 3
Handling Profile options | 2022-02-25 | 2022-02-27 | 3
Student Dashboard | 2022-02-28 | 2022-03-04 | 5
Mentor Dashboard | 2022-03-05 | 2022-03-10 | 6
Testing Students & Mentors Functionality | 2022-03-11 | 2022-03-13 | 3
Adding Resources Section | 2022-03-14 | 2022-03-16 | 3
Testing Resources Section | 2022-03-17 | 2022-03-18 | 2
Formulas:
Start Date = [End Date, row above]+1